PACKS

AI Budtender: Building a New Stack In-House

What it takes for PACKS to build, run and maintain its own talking budtender

Scope Brief, Draft 1  ·  October 15, 2026  ·  Companion to the LumiLink AI Concierge scope

Summary

| The ask | A talking AI budtender on packsclub.com, built and owned by PACKS instead of LumiLink. |
| --- | --- |
| What gets built | PACKS's own ElevenLabs agent shown as a realistic AI-generated human, streamed live by an avatar provider. A Cloudflare Worker backend and live per-store stock from AIQ Dispense. |
| Effort | 48-69 hours from one developer, about 3 weeks. |
| Running cost | About $0.18-0.31 per conversation minute plus about $120-205/month in plans. |
| Upkeep | 4-8 hours a month, carried by PACKS's one developer. |
| The call | About the same effort as the LumiLink route (46-68 hours in all). LumiLink comes out ahead only if other clients share the upkeep. |

Effort

One developer, Claude-assisted. Hours include build and testing.

| Module | Hrs |
| --- | --- |
| Accounts and setup | 2-3 |
| Avatar provider bake-off and custom AI human | 6-8 |
| Session token server | 4-6 |
| Website embed (Shopify theme) | 7-10 |
| Lip sync to the agent's audio | 3-4 |
| Persona, guardrails, red-team set | 10-14 |
| Store knowledge | 2-3 |
| Menu tool (AIQ Dispense) | 2-4 |
| Transcripts, kill switch, usage report | 4-6 |
| Languages | 3-4 |
| Load, real-phone testing, launch QA | 5-7 |
| TOTAL | 48-69 (excludes provider wait and legal review) |

Calendar: about 3 weeks next to other work; a demo on a stock AI human in week one. The custom avatar and counsel review set launch.

Ceiling: about 85-125 hours if the mobile Safari embed slips.

What in-house skips: the multi-client dashboard, billing and the add-on fee.

Cost

| Line | Type | Amount |
| --- | --- | --- |
| Voice agent minutes and LLM tokens | Variable | $0.085-0.125/min |
| Avatar streaming | Variable | $0.09-0.18/min |
| Avatar provider plan | Recurring | About $99/month |
| ElevenLabs plan | Recurring | $22-99/month by tier |
| Cloudflare Workers | Recurring | $0-5/month |
| Custom PACKS avatar | One-time | Provider quote, not yet known |
| Total per conversation minute |  | $0.18-0.31 |
| Example: 1,000 four-minute chats a month |  | $720-1,240 plus about $120-205 in plans |

Not counted here: internal build hours, monthly upkeep hours, counsel's review.

Upkeep

Estimates, not measured. This is the work PACKS carries every month after launch.

| Task | Hrs/month |
| --- | --- |
| Provider SDK, API and model changes | 1-2 |
| Prompt and guardrail tuning from transcripts | 1-2 |
| Compliance spot-check of transcripts | 1-2 |
| Menu feed breakages, store and deal updates | 0.5-1 |
| Usage, caps and cost monitoring | 0.5-1 |
| TOTAL | 4-8 |

On LumiLink: the first, fourth and fifth rows are shared once other clients join; until then the same hours land on LumiLink.

Rules and Risks

One developer: if that person is out, nobody fixes an outage or a guardrail slip; the same holds on LumiLink if one developer runs it.

California: no medical or effect claims, 21+ gate, recording and AI disclosure; counsel reviews.

Open to the public: no login, so minute caps and rate limits ship on day one.

Menu platform: built on AIQ Dispense; the Flowhub swap costs 4-6 more hours.

Next Steps

Leadership: compare this with the LumiLink scope and pick a path.

PACKS brand: the avatar's look, name, personality and languages.

Developer: confirm the Dispense proxy Worker is deployed; get avatar provider quotes.

Counsel: review the guardrail script and disclosures before launch.

Sources: PACKS theme and Dispense proxy Worker; AIQ Dispense Blueprint API; LumiLink codebase and build history; Akapulu avatar price index, LiveAvatar, D-ID docs, ElevenLabs and Cloudflare pricing pages. Accessed October 14, 2026. Prices are published ranges, not quotes; re-check before committing a budget.