LumiLink

AI Concierge: A Talking Avatar on the Website

A virtual budtender that speaks, answers and recommends in any language

Scope Brief, Draft 2  ·  October 15, 2026

Summary

| The ask | A website avatar like the reel's virtual budtender: trained on the store, guardrailed, with a set personality and a custom look. |
| --- | --- |
| What gets built | A LumiLink add-on: our existing ElevenLabs agent (voice, 30+ languages, knowledge base, product lookup) with a licensed avatar face streamed on the site. |
| Effort | 38-54 hours for the LumiLink add-on, then 8-14 to launch it for PACKS; about 2 weeks. |
| Running cost | About $0.18-0.31 per conversation minute, plus about $99/month for the avatar vendor. |
| Blocker | Avatar vendor not chosen; custom-avatar fee and streaming rates need quotes. |
| Recommendation | Build it under LumiLink and launch PACKS as the first client, not as a separate in-house build. |

Effort

One developer, Claude-assisted, at the pace of our SEO and Outbound builds. Hours include build and testing.

| Module | Hrs |
| --- | --- |
| Avatar vendor bake-off (LiveAvatar vs D-ID) and custom avatar creation | 6-8 |
| Website embed: secure session token, avatar player, mic, text fallback, mobile | 6-9 |
| Connect the ElevenLabs agent's audio to the avatar's lip sync | 3-4 |
| Persona and guardrail profile, plus a red-team test set | 7-10 |
| Store knowledge: reuse knowledge base and product lookup, add a recommendation tool | 2-4 |
| Language detection and testing in the top 5 customer languages | 3-4 |
| Dashboard: avatar and persona settings, kill switch, transcripts, minute caps | 4-5 |
| Add-on billing, entitlement and pricing page | 1-2 |
| Load, concurrency and launch QA | 6-8 |
| TOTAL, LumiLink add-on | 38-54 (excludes vendor wait and legal review) |

Basis: SEO was scoped at 173-210 hours and its code shipped in a week; Outbound's first three phases took one day.

Ceiling: the original estimate was 82-118 hours; budget against it if the mobile embed slips.

Cost

| Line | Type | Amount |
| --- | --- | --- |
| ElevenLabs agent minutes plus LLM tokens | Variable | $0.085-0.125/min |
| Avatar streaming (face only) | Variable | $0.09-0.18/min |
| Avatar vendor plan | Recurring | About $99/month |
| Custom avatar creation | One-time | Vendor quote, not yet known |
| Total per conversation minute |  | $0.18-0.31 (a 4-minute chat costs $0.70-1.22) |

Rules and Risks

Cannabis: no medical or effect claims, a 21+ gate before the avatar talks, counsel review before launch.

Health data: shoppers will describe conditions; transcripts need retention limits and a privacy notice.

Cost runaway: video costs about double voice per minute; per-client minute caps ship on day one.

PACKS: On LumiLink or In-House

The same budtender for PACKS, built two ways. Upkeep figures are our estimates.

|  | On the LumiLink stack | Built in-house at PACKS |
| --- | --- | --- |
| Build hours for PACKS | 8-14, after the add-on ships | 45-65; rebuilds knowledge base, product sync, logging |
| Monthly upkeep | 1-2 hrs PACKS-specific; platform upkeep shared | 4-8 hrs, carried alone |
| Vendor or model change | LumiLink fixes it once for every client | PACKS fixes its own copy |
| Running cost | Per-minute usage plus a LumiLink add-on fee | Same usage plus its own vendor plans |
| Owner | LumiLink; PACKS sets persona, look and menu | PACKS's developers |
| Cost of the choice | Depends on LumiLink's roadmap and pricing | No shared fixes; one client carries all upkeep |

Next Steps

Leadership: approve the LumiLink route and set the add-on price.

LumiLink dev: run the vendor bake-off and get custom-avatar and streaming quotes.

PACKS: choose the avatar's look and name; confirm the menu data source now that AIQ is going.

Counsel: review the cannabis guardrail script before PACKS goes live.

Sources: LumiLink codebase and git history; Akapulu avatar price index, LiveAvatar, D-ID docs, Macha ElevenLabs pricing. Accessed October 14, 2026. Avatar prices are published ranges, not quotes; re-check before committing a budget.